## Sheet1
Use this template to set out your milestones at each stage of your onboarding. Keep track of your milestone status, your anticipated and actual completion timeline, and the resources you'll need in order to achieve each task. You can then use this timeline to provide updates to shareholders on your progress. *NOTE: Examples provided are not based on a real implementation. Do not rely on these as a standard timeline for your onboarding with Marketo, as every implementation is unique with different milestones and requirements.
Topic | Milestone | Status | Anticipated Date | Actual Date | Resources Needed
Use these general onboarding topics to organize the stages of your milestones. | Write out your specific milestone tasks. | What is the current status of your task? | What is the aniticipated completion date of this task? | When was this task actually completed? | What resources will you need to complete this task and which team(s) will you need them from?
Admin Setup
| EXAMPLE: Create additional Marketo Users | Complete | 2018-08-27 | 2018-09-15 | Input from each team using Marketo on program types and organization needs
| EXAMPLE: Define folder structure and naming conventions | Complete | 2018-09-07 | 2018-09-12 | Information from Marketing Manager on who needs access to Marketo
Technical Setup
| EXAMPLE: Set up Authorized Support Contacts | Complete | 2018-09-05 | 2018-09-12 | None
| EXAMPLE: Set up Domain Keys Identified Mail (DKIM) for deliverability | Complete | 2018-09-15 | 2018-09-18 | Support and guidance from IT Team
CRM Integration
| EXAMPLE: Determine field mapping prior to sync | In Progress | 2018-10-22 | N/A | Support from CRM admin to understand available fields
| EXAMPLE: Conduct a data audit | In Progress | 2018-10-26 | N/A | Support from CRM admin or budget
Operational Program Build
| EXAMPLE: Create program to standardize incoming data | Not Started | 2018-11-09 | N/A | Support from Sales Ops team to set a data management strategy
| EXAMPLE: Create an email subscription center | Not Started | 2018-11-19 | N/A | Input from the marketing teams on segmentation for maliing lists
First Marketing Program Build
| EXAMPLE: Set up basic email program | In Progress | 2018-11-12 | N/A | Creative assets from digital team for emails and landing pages
| EXAMPLE: Create program for quarterly newsletter | Not Started | 2018-11-30 | N/A | Content from marketing team for newsletter email
User Training and Documentation
| EXAMPLE: Create a governance guide for internal users | Not Started | 2018-11-23 | N/A | Budget from team to contract this project out
| EXAMPLE: Train 4 users and provide them with Standard Marketo User access | Not Started | 2018-12-07 | N/A | Support from VP of Marketing to make trainings mandatory for access to Marketo
Go-Live
| EXAMPLE: Send first newsletter | Not Started | 2018-12-03 | N/A | None
| EXAMPLE: Pull first Email Metrics Report | Not Started | 2018-12-05 | N/A | None